## Timeline
| Assignee | Tue | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Total
|  | 2017-10-03 | 2017-10-04 | 2017-10-05 | 2017-10-06 | 2017-10-07 | 2017-10-08 | 2017-10-09 | 2017-10-10 | 2017-10-11 | 2017-10-12 | 2017-10-13 | 2017-10-14 | 2017-10-15 | 2017-10-16 | 2017-10-17 | 2017-10-18 | 2017-10-19 | 2017-10-20 | 2017-10-21 | 2017-10-22 | 2017-10-23 | 2017-10-24 | 2017-10-25 | 2017-10-26 | 2017-10-27 | 2017-10-28 | 2017-10-29 | 2017-10-30 | 2017-10-31
Thanksgiving Break | bar: 2017-10-07 to 2017-10-08
Midterm Week | bar: 2017-10-16
Team Unavailability
Trevor |  | 2017-10-07: Can work from home; 2017-10-14: Reduced availability due to midterms
Brendan |  | 2017-10-07: Can work from home
Rushil |  | 2017-10-05: Tron Days
Daniel |  | 2017-10-27: Not available
Ben
General Tasks | [30 empty] | 18.5
Finalize Design | All | 2017-10-04: 1; 2017-10-05: 1; 2017-10-06: 2
Finalize BOM | All | 2017-10-14: 0.5
Verify BOM | All | bar: 2017-10-14
Order Parts | bar: 2017-10-14
Planned Part Arrival |  | 2017-10-10: 0.5; 2017-10-11: 0.5
Test & Debug | All | 2017-10-27: 2; 2017-10-28: 3; 2017-10-29: 3; 2017-10-30: 1
Competition | All | 2017-10-31: 2
Mechanical Tasks | [30 empty] | 6
Finalize CAD | Trevor, Brendan | 2017-10-07: 2; 2017-10-15: 1
Machine Chassis | Trevor, Brendan | bar: 2017-10-17
Assemble Robot | Trevor, Brendan | 2017-10-21: 2
Electrical Tasks | [30 empty] | 6
Design Electrical Circuit | Rushil, Daniel | 2017-10-03: -; 2017-10-04: -; 2017-10-05: 0.5; 2017-10-06: 0.5; 2017-10-07: 3
Build Drive Circuit | Rushil, Daniel | 2017-10-10: 2
Build Sensor Circuit | Rushil, Daniel | bar: 2017-10-11 to 2017-10-14
Build R2R Bridge | Rushil, Daniel | bar: 2017-10-12 to 2017-10-17
Assemble Speaker Circuit | Rushil, Daniel | bar: 2017-10-15 to 2017-10-18
Software Tasks | [30 empty] | 25.5
Design State Machine | Ben | bar: 2017-10-04 to 2017-10-06
Outline Code | Ben | bar: 2017-10-09; 2017-10-11 to 2017-10-12
Implement Drive Code | Ben | 2017-10-13: 1; 2017-10-14: 2; 2017-10-15: 1; 2017-10-16: 0.5
Implement Line Follower Code | Ben | 2017-10-18: 0.5; 2017-10-19: 0.5; 2017-10-20: 0.5; 2017-10-21: 2
Implement Speaker Code | Ben | 2017-10-22: 1.5; 2017-10-23: 1; 2017-10-25: 1
Bug Fixes | Ben | 2017-10-26: 1; 2017-10-27: 2; 2017-10-28: 2; 2017-10-29: 2; 2017-10-30: 1
Estimated Daily Hours |  | 0 | 2 | 2.5 | 3.5 | 5 | 0 | 1 | 2.5 | 1.5 | 1 | 1 | 4.5 | 2 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 4 | 1.5 | 1 | 0 | 1 | 1 | 4 | 5 | 5 | 2 | 2 | 56
(This should be a high estimate, probably won't take nearly as long)
2018-03-30 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE

## Materials Bought
Part | Quantity | Unit Quantity | Unit Cost | Cost | Unit Weight | Weight | Order # | Link | Extra Notes |  | Total Cost | Total Weight | Cost Per Person (Before Shipping)
Main Electrical System | [9 empty] | CAD | 141.66 | 324.2258 | 28.332
Teensy LC | 1 | 1 | 14.94 | 14.94 | 3 | 3 | 1 | http://www.robotshop.com/ca/en/teensy-lc-usb-microcontroller-development-board.html |  | Order # 2 tot | 137.31 |  | 27.462
Teensy Header Pin Kit | 1 | 1 | 2.31 | 2.31 |  | 0 | 1 | http://www.robotshop.com/ca/en/break-away-headers-straight.html |  | Order #3 tot | 19.25+ wood and cut
5v Regulator | 1 | 1 | 1.12 | 1.12 | 0.1 | 0.1 | 1 | http://www.robotshop.com/ca/en/lm78m05-voltage-regulator.html |  |  | General Notes:
9 Volt Battery | 4 | 1 | 1.91 | 7.64 | 45 | 180 | 1 | http://www.robotshop.com/ca/en/9v-alkaline-battery.html |  |  | Be sure to list all prices in CAD
9v battery terminals | 2 | 1 | 0.64 | 1.28 | 0.06 | 0.12 | 1 | http://www.robotshop.com/ca/en/9v-battery-bh-06.html
Jumper Cables | 1 | 65 | 5.06 | 5.06 |  | 0 | 1 | http://www.robotshop.com/ca/en/65-22-gauge-assorted-jumper-wires.html
|  | 1 |  | 0 |  | 0 |  |  | Order #1 Verified By: Daniel
Breadboard | 1 | 1 | 4 | 4 |  | 0 | 2 | RidgidWare | one from Rushil
|  | 1 |  | 0 |  | 0 |  |  | Order #2
|  | 1 |  | 0 |  | 0
|  | 1 |  | 0 |  | 0
|  | 1 |  | 0 |  | 0
Subtotals |  |  |  | 36.35 |  | 183.22
Drive System
Motors | 2 | 1 | 15.59 | 31.18 | 18 | 36 | 1 | http://www.robotshop.com/ca/en/6v-2101-75rpm-micro-metal-gearmotor-encoder.html | https://www.pololu.com/product/2371/specs
Motor Brackets | 1 | 2 | 5.95 | 5.95 | 0.7 | 1.4 | 1 | http://www.robotshop.com/ca/en/pololu-micro-motor-mount.html
Motor Controller | 1 | 1 | 10.09 | 10.09 | 35 | 35 | 1 | http://www.robotshop.com/ca/en/l298-dual-h-bridge-dc-motor-controller.html#Useful-Links
Wheels | 1 | 2 | 6.38 | 6.38 | 11.3398 | 22.6796 | 1 | http://www.robotshop.com/ca/en/pololu-wheel-40-x-7mm-black-pair.html
Casters | 2 | 1 | 3.45 | 6.9 | 7.0874 | 14.1748 | 1 | http://www.robotshop.com/ca/en/pololu-ball-caster-3-4-in-metal-ball.html#Dimensions
Chassis (wood) | 1 | 1 | 1 | 1 | 31.7515 | 31.7515 | 0 | Laser cut, 1/8" Ply. WatIMake
|  | 1 |  | 0 |  | 0 |  |  | Order #1 Verified By: Trevor & Brendan
M3 Standoffs | 3 | 4 | 3 | 9 |  | 0 | 2 | RidgidWare
|  | 1 |  | 0 |  | 0 |  |  | Order #2
|  | 1 |  | 0 |  | 0
Subtotals |  |  |  | 70.5 |  | 141.0058
Line Follower System
Gravity Grayscale Sensor | 3 | 1 | 5.77 | 17.31 | 5 | 15 | 1 | http://www.robotshop.com/ca/en/gravity-grayscale-sensor.html
3.3v Voltage Regulator | 1 | 1 | 2.5 | 2.5 | 6 | 6 | 1 | http://www.robotshop.com/ca/en/ld1117v33-voltage-regulator.html
|  | 1 |  | 0 |  | 0 |  |  | Order #1 Verified By: Daniel
|  | 1 |  | 0 |  | 0
|  | 1 |  | 0 |  | 0
|  | 1 |  | 0 |  | 0
|  | 1 |  | 0 |  | 0
|  | 1 |  | 0 |  | 0
|  | 1 |  | 0 |  | 0
|  | 1 |  | 0 |  | 0
Subtotals |  |  |  | 19.81 |  | 21
Sound Emitter System
Speaker | 1 | 1 | 2.5 | 2.5 | 26.4 | 26.4 | 1 | http://www.robotshop.com/ca/en/speaker-pcb-mount.html
OpAmp | 1 | 1 | 6.35 | 6.35 |  | 0 | 1 | http://www.robotshop.com/ca/en/sfe-opamp-breakout.html
|  | 1 |  | 0 |  | 0 |  |  | Order #1 Verified By: Rushil
OpAmp | 1 | 1 | 2 | 2 |  | 0 | 2 | RidgidWare
Potentiometer | 1 | 1 | 0.75 | 0.75 |  | 0 | 2 | RidgidWare
10Kohm resistors | 32 | 1 | 0.1 | 3.2 |  | 0 | 2 | RidgidWare
Capacitors | 2 | 1 | 0.1 | 0.2 |  | 0 | 2 | RidgidWare
|  | 1 |  | 0 |  | 0 |  |  | Order #2
|  | 1 |  | 0 |  | 0
|  | 1 |  | 0 |  | 0
|  | 1 |  | 0 |  | 0
|  | 1 |  | 0 |  | 0
Subtotals |  |  |  | 15 |  | 26.4

## Payment
Order | Date | Final Amount Paid | Payment Made By | Estimated Delivery Date | Received | Notes
#1 - Primary Parts | 2017-10-14 | 137.31 | Brendan
#2 - Add'l Parts |  | 16.15 | Trevor
#0 - Wood |  | 1 | Trevor
0
| Amount Spent | Amount Owed | Amount Due | Amount Paid | Amount Refunded | Balance
Trevor | 17.15 | 0 | 13.742 | 27.46 | 0 | 13.718
Brendan | 137.31 | 106.418 | 0 | 0 | 110.38 | -3.962
Rushil | 0 | 0 | 30.892 | 28 | 0 | -2.892
Daniel | 0 | 0 | 30.892 | 27.46 | 0 | -3.432
Ben | 0 | 0 | 30.892 | 27.46 | 0 | -3.432
0
| Total Spent | 154.46 | Total Due | 106.418 | 0
| Amount Owed By Each | 30.892 | Total Pooled | 110.38

## BoM
RoboSympony
Part | Quantity | Unit Quantity | Unit Cost | Cost | Unit Weight | Weight | Link | Total Cost (CAD) | Total Weight
Main Electrical System | [7 empty] | 131.32 | 230.4658
Teensy LC | 1 | 1 | 14.94 | 14.94 | 3 | 3 | http://www.robotshop.com/ca/en/teensy-lc-usb-microcontroller-development-board.html
Teensy Header Pin Kit | 1 | 1 | 2.31 | 2.31 |  | 0 | http://www.robotshop.com/ca/en/break-away-headers-straight.html
9 Volt Battery | 1 | 1 | 1.91 | 1.91 | 45 | 45 | http://www.robotshop.com/ca/en/9v-alkaline-battery.html
9v battery terminals | 1 | 1 | 0.64 | 0.64 | 0.06 | 0.06 | http://www.robotshop.com/ca/en/9v-battery-bh-06.html
Jumper Cables | 1 | 65 | 5.06 | 5.06 |  | 0 | http://www.robotshop.com/ca/en/65-22-gauge-assorted-jumper-wires.html
Breadboard | 2 | 1 | 4 | 8 |  | 0 | RidgidWare
Subtotals |  |  |  | 32.86 |  | 48.06
Drive System
Motors | 2 | 1 | 15.59 | 31.18 | 18 | 36 | http://www.robotshop.com/ca/en/6v-2101-75rpm-micro-metal-gearmotor-encoder.html
Motor Brackets | 1 | 2 | 5.95 | 5.95 | 0.7 | 1.4 | http://www.robotshop.com/ca/en/pololu-micro-motor-mount.html
Motor Controller | 1 | 1 | 10.09 | 10.09 | 35 | 35 | http://www.robotshop.com/ca/en/l298-dual-h-bridge-dc-motor-controller.html#Useful-Links
Wheels | 1 | 2 | 6.38 | 6.38 | 11.3398 | 22.6796 | http://www.robotshop.com/ca/en/pololu-wheel-40-x-7mm-black-pair.html
Casters | 2 | 1 | 3.45 | 6.9 | 7.0874 | 14.1748 | http://www.robotshop.com/ca/en/pololu-ball-caster-3-4-in-metal-ball.html#Dimensions
Chassis (wood) | 1 | 1 | 1 | 1 | 31.7515 | 31.7515 | Laser cut, 1/8" Ply. WatIMake
M3 Standoffs | 3 | 4 | 3 | 9 |  | 0 | RidgidWare
Subtotals |  |  |  | 70.5 |  | 141.0058
Line Follower System
Gravity Grayscale Sensor | 3 | 1 | 5.77 | 17.31 | 5 | 15 | http://www.robotshop.com/ca/en/gravity-grayscale-sensor.html
Subtotals |  |  |  | 17.31 |  | 15
Sound Emitter System
Speaker | 1 | 1 | 2.5 | 2.5 | 26.4 | 26.4 | http://www.robotshop.com/ca/en/speaker-pcb-mount.html
OpAmp | 2 | 1 | 2 | 4 |  | 0 | RidgidWare
Potentiometer | 1 | 1 | 0.75 | 0.75 |  | 0 | RidgidWare
10Kohm resistors | 32 | 1 | 0.1 | 3.2 |  | 0 | RidgidWare
Capacitors | 2 | 1 | 0.1 | 0.2 |  | 0 | RidgidWare
Subtotals |  |  |  | 10.65 |  | 26.4